## Sheet1
Week | Date | Interest | Research Task | Motivation | Period
1 | 15th May | Test and Project | N/A | Need to complete course work | Block 2
2 | 22nd May | Project and Exam | N/A | Exams begin | Exams
3 | 29th May | AML Exam | N/A | June Exams | Exams
4 | 5th Jun | IP Exam | N/A | June Exams | Exams
5 | 12th Jun |  | Begin programming game supervisor | Have a week free to begin most important component. All AIs rely on a proper programatic model of the game domain. | Exams
6 | 19th Jun | HPC Exam | N/A | Final June exam. Have a week to study for it. | Exams
7 | 26th Jun |  | Finish game supervisor | The supervisor and game rules have to be implemented before an AI development can be done. | Break
8 | 3rd Jul |  | Begin development of standard MCTS AI | MCTS is the easiest implementation of the three major types of AI tree search algorithms being investigated. | Break
9 | 10th Jul | Birthday | Continue development of MCTS AI |  | Break
10 | 17th Jul |  | Finish development of MCTS AI | All tree AI algorithms have underlying structure and method which are similar. The first AI will take longer to implement correctly and sucsessive Ais will be easier to make as problems are discovered and solved. | Break
11 | 24th Jul |  | Start development on Minimax AI | The Hybrid AI can only be built once both the individual Ais are built. | Block 3
12 | 31st Jul |  | Finish development of Minimax AI | This AI should be quicker to develop than previous AIs. | Block 3
13 | 7th Aug |  | Start development of Hybrid AI | This is the most critical development phase as this is the heart of the research. | Block 3
14 | 14th Aug |  | Finish development of the Hybrid AI | This must be complete before analysis of the research can take place. | Block 3
15 | 21st Aug |  | Run experimental tests using AIs and collect data | These tests will be lengthy as large enough sample data must be collected before accurate results can be found. | Block 3
16 | 28th Aug |  | Run experimental tests using AIs and collect data | Continued tests as these experiments may take days to run. | Block 3
17 | 4th Sep |  | Run experimental tests using AIs and collect data | An extra week to validate and tweak any experiments which may not be producing sane results. | Block 3
18 | 11th Sep |  | Interpret results and begin to write report. | The report will take a few weeks to write. | Vacation
19 | 18th Sep |  | Continue to write report | Depending on the results the difficulty in interpretation may be different. | Block 4
20 | 25th Sep |  | Finish report | The report should be finished a few weeks early | Block 4
21 | 2nd Oct | Away on weekend | Extra time for research | Extra time allocated in case something goes wrong or for supervisor to provide feedback. | Block 4
22 | 9th Oct |  | Extra time for research | Extra time allocated in case something goes wrong or for supervisor to provide feedback. | Block 4
23 | 16th Oct |  | Research Project Should be complete | Middle of October is when the project should be completed. | Block 4
24 | 23rd Oct |  |  |  | Block 4
25 | 30th Oct | Report submission |  | The submission of final documentation is the beginning of November. | Block 4